## Deliverables & Timelines
Name of Chapter Event Event Work Plan
● Project Manager:
● Project Leaders:
● Project Team Members:
Deliverables and Associated Project Tasks |  | Owner | Contributors | Effort Hrs | Due Date | Status | Actual | Deliverable Description / Risk Responses / Notes
Program Implementation
Strategic Planning for Program
1 | Confirm interest in event/topic |  |  |  | 2012-01-01 | Not Started | 2012-01-01
2 | Hold initial meeting to discuss "owner" roles and responsibilities, and next steps |  |  |  | 2012-01-01 | Not Started | 2012-01-01
3 | Confirm collaborators/contributors and discuss contract any necessary contracts |  |  |  | 2012-01-01 | Not Started | 2012-01-01
4 | Hold meeting with collaborators/contributors |  |  |  | 2012-01-01 | Not Started | 2012-01-01
5 | Develop workplan and budget |  |  |  | 2012-01-01 | Not Started | 2012-01-01
6 | Share workplan and budget with all collaborators/contributors |  |  |  | 2012-01-01 | Not Started | 2012-01-01
7 | Define and distribute roles and responsibilities for all owners and collaborators/contributors |  |  |  | 2012-01-01 | Not Started | 2012-01-01
8 | Finalize any necessary partnership/working agreements |  |  |  | 2012-01-01 | Not Started | 2012-01-01
Program Rollout
1 | Identify program presenters |  |  |  | 2012-01-01 | Not Started | 2012-01-01
2 | Identify location |  |  |  | 2012-01-01 | Not Started | 2012-01-01
3 | Identify date/time of event |  |  |  | 2012-01-01 | Not Started | 2012-01-01
4 | Create template for invitation distribution |  |  |  | 2012-01-01 | Not Started | 2012-01-01
5 | Confirm individual/group/location pricing options |  |  |  | 2012-01-01 | Not Started | 2012-01-01
6 |  |  |  |  | 2012-01-01 | Not Started | 2012-01-01
Speaker Mangement
1 | Invite speakers, include speaker agreement |  |  |  | 2012-01-01 | Not Started | 2012-01-01
2 | Collect speaker agreement |  |  |  | 2012-01-01 | Not Started | 2012-01-01
3 | Confirm needed arangements for speaker hotels / flights |  |  |  | 2012-01-01 | Not Started | 2012-01-01
4 | Collect presenter materials |  |  |  | 2012-01-01 | Not Started | 2012-01-01
5 |  |  |  |  | 2012-01-01 | Not Started | 2012-01-01
6 |  |  |  |  | 2012-01-01 | Not Started | 2012-01-01
Location Logistics
1 | Sign hotel agreement |  |  |  | 2012-01-01 | Not Started | 2012-01-01
2 | Confirm food/beverage for meeting |  |  |  | 2012-01-01 | Not Started | 2012-01-01
3 | Confirm A/V needs for meeting |  |  |  | 2012-01-01 | Not Started | 2012-01-01
4 | Confirm signage for meeting |  |  |  | 2012-01-01 | Not Started | 2012-01-01
5 |  |  |  |  | 2012-01-01 | Not Started | 2012-01-01
6 |  |  |  |  | 2012-01-01 | Not Started | 2012-01-01
Registration
1 | Online registration set-up |  |  |  | 2012-01-01 | Not Started | 2012-01-01
2 | Reporting: ongoing, pre-event list, post-event list |  |  |  | 2012-01-01 | Not Started | 2012-01-01
3 | Badges |  |  |  | 2012-01-01 | Not Started | 2012-01-01
4 | Meeting to review reg procedures for onsite volunteers |  |  |  | 2012-01-01 | Not Started | 2012-01-01
5 |  |  |  |  | 2012-01-01 | Not Started | 2012-01-01
6 |  |  |  |  | 2012-01-01 | Not Started | 2012-01-01
Marketing
1 | Create prospective sponsor outreach materials |  |  |  | 2012-01-01 | Not Started | 2012-01-01
2 | Identify and collect marketing/email lists for target audiences |  |  |  | 2012-01-01 | Not Started | 2012-01-01
3 | Initiate PR efforts to specific publications/audiences/social media channels |  |  |  | 2012-01-01 | Not Started | 2012-01-01
4 | Create promotional copy/ad/website banner (and vanity URL/redirect, if apppropriate) |  |  |  | 2012-01-01 | Not Started | 2012-01-01
5 | Design registration form that can be downloaded from website and included in one-pager for audiences (if needed for pass-through) |  |  |  | 2012-01-01 | Not Started | 2012-01-01
6 | Announce to chapter members |  |  |  | 2012-01-01 | Not Started | 2012-01-01
7 | Establish presence/details on website with link to online registration and downloadable PDF registration form |  |  |  | 2012-01-01 | Not Started | 2012-01-01
8 | Send targeted broadcast emails to extended audinces announcing event (continue on a regular basis, adding as new lines in project plan, until date of event) |  |  |  | 2012-01-01 | Not Started | 2012-01-01
9 | Post details/updates/registration info to chapter website, LMA Connect and other social media/outreach channels |  |  |  | 2012-01-01 | Not Started | 2012-01-01
10 | Share e-marketing kits and tips/suggestions with chapter leadership and speakers, if apppropriate |  |  |  | 2012-01-01 | Not Started | 2012-01-01
11 | Include short article in LMABrienfs wiith link to website (send new briefs to HQ monthly, adding new lines in project plan, until date of event) |  |  |  | 2012-01-01 | Not Started | 2012-01-01
12 | Send save-the-date postcard, if necessary |  |  |  | 2012-01-01 | Not Started | 2012-01-01
13 | Send one-page promotion (could be electronic) to chahpter members so they can pass-through to extended audiences in their firms/companies |  |  |  | 2012-01-01 | Not Started | 2012-01-01
14 | Highlight/discuss upcoming programming during chapter meetings |  |  |  | 2012-01-01 | Not Started | 2012-01-01
15 | Analyze effectiveness of messaging/outreach and adjust messaging, if needed |  |  |  | 2012-01-01 | Not Started | 2012-01-01
16 | Personal outreach by chapter leadership (i.e., phone calls) if needed -- if attendance is low, ask chapter members to personally reach out to members or others in their own organizations, as/if appropriate |  |  |  | 2012-01-01 | Not Started | 2012-01-01
17 | Final registration reminder goes out via broadcast email |  |  |  | 2012-01-01 | Not Started | 2012-01-01
18 | Send email to registered attendees with any final updates, directions to location, etc. |  |  |  | 2012-01-01 | Not Started | 2012-01-01
19 | Issue post-event press release |  |  |  | 2012-01-01 | Not Started | 2012-01-01
20 |  |  |  |  | 2012-01-01 | Not Started | 2012-01-01
21 |  |  |  |  | 2012-01-01 | Not Started | 2012-01-01
22 |  |  |  |  | 2012-01-01 | Not Started | 2012-01-01
23 |  |  |  |  | 2012-01-01 | Not Started | 2012-01-01
24 |  |  |  |  | 2012-01-01 | Not Started | 2012-01-01
25 |  |  |  |  | 2012-01-01 | Not Started | 2012-01-01
Onsite Experience
1 | Decide what onsite materials, if any, will be provided to attendees (guides, handouts, etc.) |  |  |  | 2012-01-01 | Not Started | 2012-01-01
2 | Finalize content for onsite materials |  |  |  | 2012-01-01 | Not Started | 2012-01-01
3 | Design onsite materials and route among pertinent contributors for review/approval |  |  |  | 2012-01-01 | Not Started | 2012-01-01
4 | Send onsite materials to print |  |  |  | 2012-01-01 | Not Started | 2012-01-01
5 | Assign individuals to lead onsite registratoin, handing out badges/materials, etc. (i.e., the registration desk responsibilities |  |  |  | 2012-01-01 | Not Started | 2012-01-01
6 | Assign individuals who will meet speakers, if necessary, and lead onsite orchestration with AV and other technical aspects of the program (i.e., the speaker/session/program responsibilities) |  |  |  | 2012-01-01 | Not Started | 2012-01-01
7 | Hold training meeting for everyone who has onsite responsibilities |  |  |  | 2012-01-01 | Not Started | 2012-01-01
8 | Once onsite, conduct a final check-in before event begins to ensure everyone's comfortable and prepared. |  |  |  | 2012-01-01 | Not Started | 2012-01-01
9 |  |  |  |  | 2012-01-01 | Not Started | 2012-01-01
10 |  |  |  |  | 2012-01-01 | Not Started | 2012-01-01
Meeting Follow Up
1 | Send follow-up message to all attendees to seek feedback (conduct an event evaluation or survey?) and share information about upcoming events |  |  |  | 2012-01-01 | Not Started | 2012-01-01
2 | Schedule follow-up call with planning committee |  |  |  | 2012-01-01 | Not Started | 2012-01-01
3 | Add nonmember attendees to database as prospects for future meetings/events |  |  |  | 2012-01-01 | Not Started | 2012-01-01
4 |  |  |  |  | 2012-01-01 | Not Started | 2012-01-01
5 |  |  |  |  | 2012-01-01 | Not Started | 2012-01-01
6 |  |  |  |  | 2012-01-01 | Not Started | 2012-01-01
Note on A8: This column lists the Area of Work, the Deliverable (by name - not task), and then the tasks associated with completing this deliverable. Tasks will produce interim deliverables which support the successful completion of the project deliverable according to the quality metrics. Tasks may be broken down into sub-tasks if desired.
Note on C8: List the Name of the person responsible for either the primary deliverable or the completion of a task producing an interim deliverable. Can be the Project Manager, Project Leader, Team Member, or Volunteer.
Note on D8: List the key project team contributors who are involved in the task completion - these may be within SmithBucklin or external resources.
Note on F8: Identify the anticipated due date for this deliverable or task.
Note on H8: List the date the task or deliverable was actually accomplished
Note on G8: Using the menu provided, identify the status of the task and deliverable.
Note on I8: Describe the deliverable and its associated quality metrics. Be as descriptive as possible. Identify any actions taken to respond to risks which were identified regarding the deliverable or its activities. Add any explanatory notes as desired.
Note on E8: Estimate the number of effort hours anticipated to be used within the activity. This can be a rough estimate with range of +/- 25% being acceptable.